## Nhóm 1
| Task | Sub Task | Pic | Status | Est (hours) | StartDate | Duedate | Priority | Description
1 | Database | Create tables
|  | Create table User | Quý | Done | 1 | 2024-01-15 | 2024-01-16 | 1 | Create a Users table to store Customer and Admin account, role 1 is Customer, 2 is Admin
|  | Create table Role |  | Done | 1 | 2024-01-15 | 2024-01-16 | 1 | Create a Addresses table to store user's address
|  | Create table Booking |  | Done | 1 | 2024-01-15 | 2024-01-16 | 1 | Create a forgot_pass table
|  | Create table Report | Duy | Done | 1 | 2024-01-15 | 2024-01-16 | 1 | Create a Products table to store products
|  | Create table Feedback |  | Done | 1 | 2024-01-15 | 2024-01-16 | 1 | Create a Categories table to store product categories
|  | Create table Product |  | Done | 1 | 2024-01-15 | 2024-01-16 | 1 | Create a Sizes table to store product sizes
|  | Create table Product Type |  | Done | 1 | 2024-01-15 | 2024-01-16 | 1 | Create a BestSeller table to store the purchased quantity of each drink
|  | Create table Contractor | Hân | Done | 1 | 2024-01-15 | 2024-01-16 | 1 | Create a view_home table
|  | Create table Project | Vy | Done | 1 | 2024-01-15 | 2024-01-16 | 1 | Create an Orders table to store all customer orders
|  | Create table Project Type |  | Done | 1 | 2024-01-15 | 2024-01-16 | 1 | Create an OrderDetails table to store multiple product options from the Orders table
|  | Create SQL Server database | Đạt | Done | 1 | 2024-01-15 | 2024-01-16 | 1 | Create and test database Undeee
2 | Models & Services | Front end
|  | Admin Page | Duy | Done | 8 | 2024-01-25 | 2024-01-29
|  | View Account |  | Done | 8 | 2024-01-25 | 2024-01-29
|  | Ban Account |  | Done | 8 | 2024-01-25 | 2024-01-29
|  | Remove Account |  | Open
|  | Booking |  | Open
|  | History | Duy | Open
|  | Create Timeshare | Hân | In Progress | 8 | 2024-01-25 | 2024-01-29
|  | View Timeshare |  | In Progress | 8 | 2024-01-25 | 2024-01-29
|  | View Profit |  | In Progress | 8 | 2024-01-25 | 2024-01-29
|  | View Feedback |  | In Progress | 8
|  | StaffPage |  | Open
Back end
|  | Controllers | Đạt | Done | 1 | 2024-01-25 |  | 1
|  | Entities |  | Done | 2 | 2024-01-25 |  | 1
|  | Config | Vy | Done |  | 2024-01-25
|  | Exceptions |  | Done | 2 | 2024-01-25 |  | 1
|  | Dtos | Đạt Quý Vy | Done |  | 2024-01-25 |  |  | Quý: Role, User, News, Report -- Đạt: Booking, Feedback, Product, Product Type -- Vy: Project, Contractor, Project type
|  | Repositories | Quý | Done | 2 | 2024-01-25 |  | 1 | Quý: Role, User, News, Report -- Đạt: Booking, Feedback, Product, Product Type -- Vy: Project, Contractor, Project type
|  | Services |  | Done | 2 | 2024-01-25 |  | 1 | Quý: Role, User, News, Report -- Đạt: Booking, Feedback, Product, Product Type -- Vy: Project, Contractor, Project type
3 | Controller & Views | Front end
|  | Home Page | Duy | Done | 8 | 2024-01-25 | 2024-01-29
|  | View Project Detail 1 |  | Done | 8 | 2024-01-25 | 2024-01-29
|  | View Project Detail 2 |  | Done | 8 | 2024-01-25 | 2024-01-29
|  | View Project |  | Done |  | 2024-02-12 | 2024-02-20
|  | View Product |  | Done |  | 2024-02-12 | 2024-02-20
|  | Create Product |  | Done |  | 2024-02-12 | 2024-02-20
|  | View Report |  | Done |  | 2024-02-12 | 2024-02-20
|  | View Feedback |  | Done |  | 2024-02-12 | 2024-02-20
|  | News |  | Done |  | 2024-02-12 | 2024-02-20
|  | View Booking |  | Done |  | 2024-02-12 | 2024-02-20
|  | Booking |  | Done |  | 2024-02-12 | 2024-02-20
|  | History | Hân | Done |  | 2024-02-12 | 2024-02-20
|  | Contact |  | Done | 8 | 2024-01-25 | 2024-01-29
|  | Log In |  | Done | 8 | 2024-01-25 | 2024-01-29
|  | Sign Up |  | Done | 8 | 2024-01-25 | 2024-01-29
|  | Admin Page |  | Done
|  | Customer Page |  | Done
|  | StaffPage |  | Done
Back end
|  | Controllers | Đạt | Done | 1 | 2024-01-25 |  | 1
|  | Entities |  | Done | 2 | 2024-01-25 |  | 1
|  | Config | Vy | Done |  | 2024-01-25
|  | Exceptions |  | Done | 2 | 2024-01-25 |  | 1
|  | Dtos | Đạt Quý Vy | Done |  | 2024-01-25 |  |  | Quý: Role, User, News, Report -- Đạt: Booking, Feedback, Product, Product Type -- Vy: Project, Contractor, Project type
|  | Repositories | Quý | Done | 2 | 2024-01-25 |  | 1
|  | Services |  | Done | 2 | 2024-01-25 |  | 1
|  | Admin | [6 empty] | xem xóa sửa các role, xem report, thống kê (số lượng user...)
|  | View Customer | Đạt | Done | 3 | 2024-02-05 |  | 1
|  | View Staff |  | Done | 3 | 2024-02-05 |  | 1
|  | View Total Staff |  | Done | 3 | 2024-02-05 |  | 1
|  | Delete Customer |  | Done | 3 | 2024-02-05 |  | 1
|  | Delete Staff |  | Done | 3 | 2024-02-05 |  | 1
|  | Change Status Staff |  | Done | 3 | 2024-02-05 |  | 1
|  | Change Status Customer |  | Done | 3 | 2024-02-05 |  | 1
|  | Customer | [6 empty] | đặt phòng, view phòng, feedback sau khi sử dụng, report user khác, ...nói chung các quyền như khách shopee
|  | View All Product | Vy | Done |  | 2024-02-12 | 2024-02-20 | 2
|  | View Product By Product Id |  | Done |  | 2024-02-12 | 2024-02-20 | 2
|  | View All Booking |  | Done |  | 2024-02-12 | 2024-02-20 | 2
|  | Create Booking |  | Done |  | 2024-02-12 | 2024-02-20 | 2
|  | Edit Booking |  | Done |  | 2024-02-12 | 2024-02-20 | 2
|  | Delete Booking |  | Done |  | 2024-02-12 | 2024-02-20 | 2
|  | View Booking By Account Id |  | Done |  | 2024-02-12 | 2024-02-20 | 2
|  | View Booking By Booking Id |  | Done |  | 2024-02-12 | 2024-02-20 | 2
|  | Delete Booking By Booking Id |  | Done |  | 2024-02-12 | 2024-02-20 | 2
|  | View All Feedback |  | Done |  | 2024-02-21 | 2024-03-01 | 2
|  | Submit Feedback |  | Done |  | 2024-02-21 | 2024-03-01 | 2
|  | Edit Feedback |  | Done |  | 2024-02-21 | 2024-03-01 | 2
|  | Delete Feedback |  | Done |  | 2024-02-21 | 2024-03-01 | 2
|  | View All Report |  | Done |  | 2024-02-21 | 2024-03-01 | 2
|  | Submit Report |  | Done |  | 2024-02-21 | 2024-03-01 | 2
|  | Update Report |  | Done |  | 2024-02-21 | 2024-03-01 | 2
|  | View All Picture |  | Done |  | 2024-02-21 | 2024-03-01 | 2
|  | Staff | [6 empty] | nngười trung gian, duyệt bài, tiếp nhận report, ban/unban account
|  | Change status Product | Đạt | Done |  | 2024-02-10 | 2024-02-20 | 2
|  | Create Account |  | Done |  | 2024-02-10 | 2024-02-20 | 2
|  | Change status Customer |  | Done |  | 2024-02-10 | 2024-02-20 | 2
|  | View Report |  | Done |  | 2024-02-10 | 2024-02-20 | 2
|  | View Product |  | Done |  | 2024-02-10 | 2024-02-20 | 2
|  | View Product By Status |  | Done |  | 2024-02-10 | 2024-02-20 | 2
|  | View Report By Id |  | Done |  | 2024-02-10 | 2024-02-20 | 2
|  | Delete Product |  | Done |  | 2024-02-10 | 2024-02-20 | 2
|  | Accpect Reject Active |  | Done |  | 2024-02-10 | 2024-02-20 | 2
|  | Search by ProductName |  | Done |  | 2024-02-10 | 2024-02-20 | 2
|  | Search by AccountName |  | Done |  | 2024-02-10 | 2024-02-20 | 2
|  | View total Customer |  | Done |  | 2024-02-10 | 2024-02-20 | 2
|  | View total Status Customer |  | Done |  | 2024-02-10 | 2024-02-20 | 2
|  | Change Status Report |  | Done |  | 2024-03-01 | 2024-03-08 | 2
|  | Create news |  | Done |  | 2024-03-02 | 2024-03-08 | 2
|  | Change status block for Account |  | Done |  | 2024-03-03 | 2024-03-08 | 2
|  | View Total Booking Report |  | Done |  | 2024-03-04 | 2024-03-08 | 2
|  | Change status for Booking |  | Done |  | 2024-03-05 | 2024-03-08 | 2
|  | owner | [6 empty] | đăng phòng, đăng bài, xem phòng đăng, chỉnh trạng thái, xem thông kế số tiền kiếm được, trả lời đánh giá khách hàng
|  |  | Quý |  |  | 2024-03-05
2024-03-06
2024-03-07
2024-03-08
2024-03-09
2024-03-10
2024-03-11